## Sheet1
415476 | 2023/05 | Ready for Deployment | 89 | Billing Invoice | [Testing] Concurrency - Office Visit List - Check-out with all other actions | Hamza Sadiq | Concurrency of Scheduler and Flowsheet | Activity Based Scheduler | Support | Release Notes mentioned in User Story 368113: Concurrency - Scheduler - Progress Note with all other | Low
394124 | 2023/05 | Ready for Deployment | 87 | Billing Invoice | As developers, we want to reduce our product's technical debt to improve our product quality. | Nauman Altaf | Technical Debt - SonarQube bugs removal | 10g Improvements | NA | Internal Story | Low
393121 | 2023/05 | Ready for Deployment | 87 | Billing Invoice | Change system behavior when CPT DOS Does Not Lie in Its Effective Period (Bulk Charge/Bulk Review) | Abdur Rehman Shamsi | Marking CPT as inactive if DOS lies outside its Effective Dates | Enhancing Procedure Settings in 10g | Client | Post Title: Restrict/Notify User when Service Date lies outside a Procedure’s Effective PeriodPost D | Low
368150 | 2023/05 | Ready for Deployment | 85 | Billing Invoice | Concurrency - Office Visit List - Check-in with all other actions | Basma Aslam | Concurrency of Scheduler and Flowsheet | Activity Based Scheduler | Support | Release Notes mentioned in User Story 368113: Concurrency - Scheduler - Progress Note with all other | Low
391440 | 2023/05 | Ready for Deployment | 87 | Billing Invoice | Concurrency - Office Visit List - Check-in with all other actions | Hiba Rashid | Concurrency of Scheduler and Flowsheet | Activity Based Scheduler | Support | Release Notes mentioned in User Story 368113: Concurrency - Scheduler - Progress Note with all other | Low
368154 | 2023/05 | Ready for Deployment | 88 | Billing Invoice | Concurrency - Office Visit List - Check-out with all other actions | Basma Aslam | Concurrency of Scheduler and Flowsheet | Activity Based Scheduler | Support | Release Notes mentioned in User Story 368113: Concurrency - Scheduler - Progress Note with all other | Low
413616 | 2023/05 | Ready for Deployment | 89 | Billing Invoice | Electronic Signature 21 CFR Part 11 - Logging via URL and CureCam > eSuperbill | Ismail Suri | Code of Federal Regulation - Electronic Signature | Business Continuity - RM2022 | NA | Post Title: 21 CFR Part 11 Compliant Electronic SignaturesPost Description:21 CFR Part 11 is a regul | Low
374563 | 2023/05 | Ready for Deployment | 85 | Billing Invoice | Electronic Signature 21 CFR Part 11 Compliant Signature > eSuperbill | Aisha Qureshi | Code of Federal Regulation - Electronic Signature | Business Continuity - RM2022 | Client | Post Title: 21 CFR Part 11 Compliant Electronic Signatures > eSuperbill Post Description:With this e | Low
397502 | 2023/05 | Ready for Deployment | 87 | Billing Invoice | Log of Expert System on Merge eSuperbill | Farhan Ajmal | Logs | Billing Development | Support | With this enhancement in cureMD solution, RCM user will able to view the merge eSuperbill logs of Ex | Low
403317 | 2023/05 | Ready for Deployment | 88 | Billing Invoice | Plan Balance not Positioned properly on Patient Banner | Abdur Rehman Shamsi | Patient Banner - Billing Portion | Billing Development | NA | Fix of a Live issue, No release notes are needed for an already existing Implementation. | Low
374828 | 2023/05 | Approved | 84 | Billing Payments | nH Refund API - Implementation for Outstanding balances and advances (deductibles) | Maham Nasir Khan | Billing APIs | CureMD API | NA | With this modification in the refund API, the user should be able to refund a patient's outstanding | Low
402463 | 2023/05 | Ready for Deployment | 87 | Billing Payments | [Refactorization] As a Payment poster, I want collapsible grouping for ERA claims | Sohaib Shahid | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
402272 | 2023/05 | Ready for Deployment | 87 | Billing Payments | [Technical] Advance Allocation with different Appointment | Asad Rajpoot | Work queue structure for payments | Batch Payments | NA | This is a technical story. No release notes are required. | Low
387752 | 2023/05 | Ready for Deployment | 89 | Billing Payments | [Technical] Appointment Notes Logging in Audit Trail | Asad Rajpoot | Logs | Billing Development | NA | For the technical story, no release notes are needed. | Low
417322 | 2023/05 | Ready for Deployment | 89 | Billing Payments | [Technical] As a developer, I want to find and cater missing Copay scenarios in ERA batches | Abdur Rehman Shamsi | Reconciling items within batches | Batch Payments | NA | Attached with User Guide | Low
381695 | 2023/05 | Ready for Deployment | 85 | Billing Payments | [TECHNICAL] Avoid the deadlock while adding/update the payments | Asad Rajpoot | Payments | Billing Development | NA | It's the technical US. No release notes required. | Low
393466 | 2023/05 | Ready for Deployment | 86 | Billing Payments | [TECHNICAL] Avoid the deadlock while adding/update the payments | Saud Jamshaid | Payments | Billing Development | NA | It's the technical US. No release notes required. | Low
397842 | 2023/05 | Ready for Deployment | 87 | Billing Payments | [Technical] Exception Handling and File logging for import diagnosis | Asad Rajpoot | Diagnosis | Billing Development | NA | This is a technical story. No release notes are required. | Low
401549 | 2023/05 | Ready for Deployment | 87 | Billing Payments | [Technical] Rework of Payerid to Planid in batch payments | Ahmad Saleem | Work queue structure for payments | Batch Payments | NA | Attached with User Guide | Low
409458 | 2023/05 | Ready for Deployment | 88 | Billing Payments | [Technical] Rework of Payerid to Planid in batch payments | Sohaib Shahid | Work queue structure for payments | Batch Payments | NA | Attached with User Guide | Low
409252 | 2023/05 | Ready for Deployment | 88 | Billing Payments | [Testing] Ability to manually invoke TextToPay Service | Asad Rajpoot | Text 2 Pay | Payment processing integration with Global Payment Gateway | Client | Post Title: Ability to manually invoke Text To Pay ServicePost Description: With this enhancement in | Low
416134 | 2023/05 | Ready for Deployment | 89 | Billing Payments | [Testing] Ability to send Text to Pay after specified days | Abdur Rehman Shamsi | Text 2 Pay | Payment processing integration with Global Payment Gateway | Client | Post Title: Ability to send Text to Pay after specified daysPost Description: With this enhancement | Low
398366 | 2023/05 | Ready for Deployment | 87 | Billing Payments | Ability to manually invoke TextToPay Service | Abdur Rehman Shamsi | Text 2 Pay | Payment processing integration with Global Payment Gateway | Client | Post Title: Ability to manually invoke Text To Pay ServicePost Description: With this enhancement in | Low
395208 | 2023/05 | Ready for Deployment | 86 | Billing Payments | Ability to manually invoke TextToPay Service | Abdur Rehman Shamsi | Text 2 Pay | Payment processing integration with Global Payment Gateway | NA | Refer to User Story 398366: Ability to manually invoke TextToPay Service | Low
405916 | 2023/05 | Ready for Deployment | 88 | Billing Payments | Ability to Restrict Payment Posting Updates | Farhan Ajmal | Payments | RCM - RM2023 | Client | Post Title: Ability to Restrict Credit Card Payments PostingPost Description: With this enhancement | Low
406847 | 2023/05 | Ready for Deployment | 88 | Billing Payments | Ability to send Text to Pay after specified days | Abdur Rehman Shamsi | Text 2 Pay | Payment processing integration with Global Payment Gateway | NA | Refer to User Story 416134: [Testing] Ability to send Text to Pay after specified days | Low
393935 | 2023/05 | Ready for Deployment | 86 | Billing Payments | As a biller, I want to open specific appointment when I click on DOS | Abdur Rehman Shamsi | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
391906 | 2023/05 | Ready for Deployment | 86 | Billing Payments | As a biller, I want to see reason behind problematic and Non-postable claims | Abdur Rehman Shamsi | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
391743 | 2023/05 | Ready for Deployment | 86 | Billing Payments | As a biller, I want to view 835 ERA file with each payment | Abdur Rehman Shamsi | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
392305 | 2023/05 | Ready for Deployment | 86 | Billing Payments | As a biller, I want to view ERA report of each claim | Abdur Rehman Shamsi | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
345172 | 2023/05 | Ready for Deployment | 85 | Billing Payments | As a developer, I want to maintain an approval status for each batch separately | Ahmad Saleem | Reviewing and closing batches | Batch Payments | NA | Attached with User Guide | Low
405510 | 2023/05 | Ready for Deployment | 89 | Billing Payments | As a payment poster, I want a settings to enable/disable auto-verification of payments | Abdur Rehman Shamsi | Payment instrument tracking | Batch Payments | NA | Attached with User Guide | Low
395985 | 2023/05 | Ready for Deployment | 87 | Billing Payments | As a payment poster, I want an option to select next responsible party on each claim of a batch | Abdur Rehman Shamsi | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
409141 | 2023/05 | Ready for Deployment | 88 | Billing Payments | As a payment poster, I want an option to select next responsible party on each claim of a batch | Saud Jamshaid | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
382079 | 2023/05 | Ready for Deployment | 86 | Billing Payments | As a Payment poster, I want collapsible grouping for ERA claims | Abdur Rehman Shamsi | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
345166 | 2023/05 | Ready for Deployment | 84 | Billing Payments | As a payment poster, I want to add and view Reconciling Items against payment batches and claims wit | Ahmad Saleem | Reconciling items within batches | Batch Payments | NA | Attached with User Guide | Low
343836 | 2023/05 | Ready for Deployment | 83 | Billing Payments | As a payment poster, I want to add claims associated with a batch | Subhan Ahmad | Editing ERA claim associations and payments | Batch Payments | NA | Attached with User Guide | Low
387208 | 2023/05 | Ready for Deployment | 86 | Billing Payments | As a payment poster, I want to attach files with a Batch | Abdur Rehman Shamsi | Allowing attachments with batches | Batch Payments | NA | Attached with User Guide | Low
364907 | 2023/05 | Ready for Deployment | 82 | Billing Payments | As a payment poster, I want to be able to search for claims associated with an ERA batch | Subhan Ahmad | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
364909 | 2023/05 | Ready for Deployment | 82 | Billing Payments | As a payment poster, I want to be able to sort claims associated with a batch | Subhan Ahmad | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
403763 | 2023/05 | Ready for Deployment | 87 | Billing Payments | As a payment poster, I want to download attach files with a Batch | Saud Jamshaid | Allowing attachments with batches | Batch Payments | NA | Attached with User Guide | Low
357990 | 2023/05 | Ready for Deployment | 82 | Billing Payments | As a payment poster, I want to identify batches with problematic and non-postable claims on the batc | Subhan Ahmad | Work queue structure for payments | Batch Payments | NA | Attached with User Guide | Low
345157 | 2023/05 | Ready for Deployment | 83 | Billing Payments | As a payment poster, I want to make changes to claims and claim details associated with an ERA | Ahmad Saleem | Editing ERA claim associations and payments | Batch Payments | NA | Attached with User Guide | Low
375800 | 2023/05 | Ready for Deployment | 85 | Billing Payments | As a payment poster, I want to post payments for claims linked to batches from the batch details scr | Subhan Ahmad | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
395914 | 2023/05 | Ready for Deployment | 88 | Billing Payments | As a payment poster, I want to record adjustments codes against all claims in a batch on a CPT level | Abdur Rehman Shamsi | Reconciling items within batches | Batch Payments | NA | Attached with User Guide | Low
416216 | 2023/05 | Ready for Deployment | 89 | Billing Payments | As a payment poster, I want to record adjustments codes against all claims in a batch on a CPT level | Aroosha Farooq | Reconciling items within batches | Batch Payments | NA | Attached with User Guide | Low
370436 | 2023/05 | Ready for Deployment | 83 | Billing Payments | As a payment poster, I want to remove claims associated with a batch | Subhan Ahmad | Editing ERA claim associations and payments | Batch Payments | NA | Attached with User Guide | Low
380369 | 2023/05 | Ready for Deployment | 84 | Billing Payments | As a payment poster, I want to remove claims associated with a batch, removing any payments posted f | Subhan Ahmad | Editing ERA claim associations and payments | Batch Payments | NA | Attached with User Guide | Low
370417 | 2023/05 | Ready for Deployment | 84 | Billing Payments | As a payment poster, I want to remove Reconciling Items against payment batches | Subhan Ahmad | Reconciling items within batches | Batch Payments | NA | Attached with User Guide | Low
380921 | 2023/05 | Ready for Deployment | 85 | Billing Payments | As a payment poster, I want to see patient details on the banner of a claim | Abdur Rehman Shamsi | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
376049 | 2023/05 | Ready for Deployment | 84 | Billing Payments | As a payment poster, I want to view copay and modifier along with CPT level details for claims assoc | Subhan Ahmad | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
393517 | 2023/05 | Ready for Deployment | 86 | Billing Payments | As a payment poster, I want to view details of previous payments received against a service from the | Zaheer Abbas | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
355640 | 2023/05 | Ready for Deployment | 81 | Billing Payments | As a Practice User, I want to access and view all insurance payments on a single screen so that I ca | Aroosha Farooq | Work queue structure for payments | Batch Payments | NA | Attached in User Guide. | Low
355717 | 2023/05 | Ready for Deployment | 81 | Billing Payments | As a Practice User, I want to apply filters on columns on the ‘Batches Queue’ So that I can retriev | Aroosha Farooq | Enhanced filter and sorting options | Batch Payments | NA | Attached with User Guide | Low
355918 | 2023/05 | Ready for Deployment | 81 | Billing Payments | As a practice user, I want to assign batches to myself So that I can view tasks in my queue separate | Aroosha Farooq | Work queue structure for payments | Batch Payments | NA | Attached with User Guide | Low
345163 | 2023/05 | Ready for Deployment | 85 | Billing Payments | As a practice user, I want to mark the payment status against each batch | Ahmad Saleem | Payment instrument tracking | Batch Payments | NA | Attached with User Guide | Low
364800 | 2023/05 | Ready for Deployment | 82 | Billing Payments | As a practice user, I want to view all claims associated with an ERA batch | Subhan Ahmad | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
364804 | 2023/05 | Ready for Deployment | 82 | Billing Payments | As a practice user, I want to view all services associated with claims within an ERA batch | Subhan Ahmad | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
364899 | 2023/05 | Ready for Deployment | 82 | Billing Payments | As a practice user, I want to view header information relevant to ERA batches created | Subhan Ahmad | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
355651 | 2023/05 | Ready for Deployment | 81 | Billing Payments | As a practice user, I want to view summaries on the batches queue, based on filtered results | Aroosha Farooq | Reporting and summaries | Batch Payments | NA | Attached with User Guide | Low
342040 | 2023/05 | Ready for Deployment | 82 | Billing Payments | As a practice user, I want to view the settlement status of each batch | Subhan Ahmad | Reconciling payments with settlements | Batch Payments | NA | Attached with User Guide | Low
383085 | 2023/05 | Ready for Deployment | 85 | Billing Payments | As a product owner, I want Batch listing in tabular form with separate ERA and EOB tabs | Abdur Rehman Shamsi | Work queue structure for payments | Batch Payments | NA | Attached with User Guide | Low
405716 | 2023/05 | Ready for Deployment | 89 | Billing Payments | As a product owner, I want changes in UI and UX of Details and listing screens | Abdur Rehman Shamsi | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
382029 | 2023/05 | Ready for Deployment | 86 | Billing Payments | As a product owner, I want changes in UI and UX of Details screens | Abdur Rehman Shamsi | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
381710 | 2023/05 | Ready for Deployment | 85 | Billing Payments | As a product owner, I want changes in UI and UX of Listing screens | Abdur Rehman Shamsi | Work queue structure for payments | Batch Payments | NA | Attached with User Guide | Low
410323 | 2023/05 | Ready for Deployment | 88 | Billing Payments | As developers, we want to reduce our product's technical debt to improve our product quality (Import | Ahmad Saleem | 10g Services Technical Debt Removal | 10g Improvements | NA | This is a technical story. No release notes are required | Low
389998 | 2023/05 | Ready for Deployment | 86 | Billing Payments | As payment poster, I want to see settled/unsettled and Reconciling amount in the KPI on details scre | Abdur Rehman Shamsi | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
387923 | 2023/05 | Ready for Deployment | 87 | Billing Payments | Audit Trial for CureBilling Page ¦ Missing scenarios | Abdur Rehman Shamsi | Curebilling Setting | RCM - RM2023 | NA | Refer to User Story 323767: Audit Trial for CureBilling page | Low
414749 | 2023/05 | Ready for Deployment | 89 | Billing Payments | Rework of Payerid to Planid in batch payments | Aroosha Farooq | Work queue structure for payments | Batch Payments | NA | Attached with User Guide | Low
405697 | 2023/05 | Ready for Deployment | 90 | Data Mining Reports | [HCFA Claims] Ability to see Log of Denials When Moved to Inprocess Bucket Through Resubmission | Abdur Rehman Shamsi | Logging/Procedure search at Denial Bucket | RCM - RM2022 | NA | This is a missing scenario of already implemented logs. No release notes needed. | Low
403328 | 2023/05 | Ready for Deployment | 90 | Data Mining Reports | Ability to search based on Preferred Language and Age in Months on Patient Search Report | Abdur Rehman Shamsi | Misc. | Business Continuity | Client | Post Title: Ability to search based on Preferred Language and Age in Months on Patient Search Report | Low
396722 | 2023/05 | Ready for Deployment | 90 | Data Mining Reports | Clinical Summary Report changes | Aisha Qureshi |  |  | NA | -- | Low
418052 | 2023/05 | Ready for Deployment | 90 | Data Mining Reports | Exclude Patients with PR-100 Adjustments from Patient Statements | Abdur Rehman Shamsi | Misc. | Business Continuity | Client | Post Title: Ability to Exclude Patients with PR-100 Adjustments from Patient StatementsPost Descript | Low
422044 | 2023/05 | Development | 90 | Quality Programs | Appointment Level Attachment Functionality on ADD Problem List | Farhan Ajmal | Problem List Resolution Automation | RCM - RM2023 | Support | With this enhancement in CureMD application, user will able to view the new design of add problem li | Low
396784 | 2023/05 | Ready for Deployment | 87 | Quality Programs | [Enhancement] As a Provider, I want to be able to view if a Patient qualifies for a MIPS CQM but the | Sheryl Manzoor | Quality - Registry 2020 | MIPS | Client | Displaying Incomplete Measures with Multiple StrataGIVEN: Quality Programs module is enabled for the | Low
353089 | 2023/05 | Ready for Deployment | 85 | Quality Programs | [Part 1: Backend] As a Provider, I want to be able to view if a Patient qualifies for a MIPS CQM but | Sheryl Manzoor | Quality - Registry 2020 | MIPS | Client | Post Title: Completing MIPS CQMs Documentation from the Patient ChartPost Description: With this enh | Low
390289 | 2023/05 | Ready for Deployment | 86 | Quality Programs | [Part 2: Frontend] As a Provider, I want to be able to view if a Patient qualifies for a MIPS CQM bu | Sheryl Manzoor | Quality - Registry 2020 | MIPS | Client | Post Title: Completing MIPS CQMs Documentation from the Patient ChartPost Description: With this enh | Low
406209 | 2023/05 | Ready for Deployment | 88 | Quality Programs | [Technical] As an analyst, I want to have all the issues resolved in the MIPS job for registry measu | Sheryl Manzoor | Quality - Registry 2020 | MIPS | Support | A release note does not need to be published on CureWiki for this user story. This user story was wr | Low
373060 | 2023/05 | Ready for Deployment | 87 | Quality Programs | [Technical] Removing yearly check for updating CCM Billing Procedure Codes Library | Sheryl Manzoor | Care Programs | MixPanel | Support | Note: Please do not publish this release note on CureWiki. This user story was written to remove yea | Low
412463 | 2023/05 | Ready for Deployment | 89 | Quality Programs | Add New Category in Problem List Issue Category dropdown List | Hamza Qaiser | Problem List Resolution Automation | RCM - RM2023 | Support | With this enhancement in CureMD application, RCM user will able to add the new issue category while | Low
397570 | 2023/05 | Ready for Deployment | 89 | Quality Programs | Appointment and Procedure wise Add Problem List Module Updates | Farhan Ajmal | Problem List Resolution Automation | RCM - RM2023 | Support | With this enhancement in CureMD application, user will able to view the new design of add problem li | Low
357440 | 2023/05 | Ready for Deployment | 86 | Quality Programs | As an analyst, I want the changes made to patient's qualification in MIPS CQMs from patient chart to | Sheryl Manzoor | Quality - Registry 2020 | MIPS | Client | Post Title: Displaying Changes Made to Patient's Qualification in MIPS CQMs from Patient Chart on th | Low
382856 | 2023/05 | Ready for Deployment | 87 | Quality Programs | Billing: Expert System's Warning/Error workflow updates on eSuperbill | Farhan Ajmal | Expert System Enhancements | RCM - RM2023 | Support | With this enhancement in CureMD application, user will able to sign the eSuperbill when Expert Syste | Low
373845 | 2023/05 | Ready for Deployment | 88 | Quality Programs | Bulk Actions on Problem List | Rabia Shahid | Problem List Resolution Automation | RCM - RM2023 | Client | With this enhancement in CureMD application. Practice User will able to perform bulk action on probl | Low
396968 | 2023/05 | Ready for Deployment | 87 | Quality Programs | Default Provider on Quick Esuperbill | Abdur Rehman Shamsi | eSuperbills | Billing Development | Client | Post Title: Default Provider unselected on Quick eSuperbillPost Description: With this enhancement i | Low
366633 | 2023/05 | Ready for Deployment | 86 | Quality Programs | Moving the appointment to OnHold when adding a Comment on a Problem from the Problem List | Muhammad Mobeen | Problem List Resolution Automation | RCM - RM2023 | Support | With this enhancement in CureMD Application, system will move the appointment automatically to on ho | Low
399893 | 2023/05 | Ready for Deployment | 87 | Quality Programs | Moving the appointment to OnHold when adding all comments or Actions | Farhan Ajmal | Problem List Resolution Automation | RCM - RM2023 | Client | With this enhancement in CureMD application, user will able to move the appointment or procedure lev | Low
397201 | 2023/05 | Ready for Deployment | 87 | Quality Programs | Need to add URL as an attachment in Problem List | Farhan Ajmal | Problem List Resolution Automation | RCM - RM2023 | Support | With this enhancement in CureMD application, user will able to attach the URL as an attachment. Curr | Low
360314 | 2023/05 | Ready for Deployment | 89 | Quality Programs | Need to enable E&M Calculator and MDM method for 99252-99255: Inpatient Consultations | Farhan Ajmal | Hospital Inpatient Categories Updates for 2023 | Evaluation and Management - 2023 | Client | Post Title: Enable E&M Method for inpateint Consultation CategoryPost Description: With this enhance | Low
395950 | 2023/05 | Ready for Deployment | 88 | Quality Programs | Need to Update Problem List Category Dropdown | Farhan Ajmal | Problem List Resolution Automation | RCM - RM2023 | Support | With this enahancement in CureMD application, User will able to search the Issue Categories while ad | Low
374177 | 2023/05 | Ready for Deployment | 87 | Quality Programs | Oncology Performance Status Assessment Forms in v10 | Abdur Rehman Shamsi | Enhancements in Assessment Component - Graphical Overview - Trend Charts | Roadmap 2022 | Client | Post Title: Ability to Record Oncology Performance Status in 10gPost Description: With this enhancem | Low
408241 | 2023/05 | Ready for Deployment | 88 | Quality Programs | SonarQube bug fixing | Rabia Shahid | Technical Debt - SonarQube bugs removal | 10g Improvements | NA | N/A | Low

## Sheet2
ID | Release | State | 'Sprints with Date'[Sprints] | Team | Story | Assigned To | Feature | Epic | Notes | Release Notes | Risk
415476 | 2023/05 | Ready for Deployment | 89 | Billing Invoice | [Testing] Concurrency - Office Visit List - Check-out with all other actions | Hamza Sadiq | Concurrency of Scheduler and Flowsheet | Activity Based Scheduler | Support | Release Notes mentioned in User Story 368113: Concurrency - Scheduler - Progress Note with all other | Low
394124 | 2023/05 | Ready for Deployment | 87 | Billing Invoice | As developers, we want to reduce our product's technical debt to improve our product quality. | Nauman Altaf | Technical Debt - SonarQube bugs removal | 10g Improvements | NA | Internal Story | Low
393121 | 2023/05 | Ready for Deployment | 87 | Billing Invoice | Change system behavior when CPT DOS Does Not Lie in Its Effective Period (Bulk Charge/Bulk Review) | Abdur Rehman Shamsi | Marking CPT as inactive if DOS lies outside its Effective Dates | Enhancing Procedure Settings in 10g | Client | Post Title: Restrict/Notify User when Service Date lies outside a Procedure’s Effective PeriodPost D | Low
368150 | 2023/05 | Ready for Deployment | 85 | Billing Invoice | Concurrency - Office Visit List - Check-in with all other actions | Basma Aslam | Concurrency of Scheduler and Flowsheet | Activity Based Scheduler | Support | Release Notes mentioned in User Story 368113: Concurrency - Scheduler - Progress Note with all other | Low
391440 | 2023/05 | Ready for Deployment | 87 | Billing Invoice | Concurrency - Office Visit List - Check-in with all other actions | Hiba Rashid | Concurrency of Scheduler and Flowsheet | Activity Based Scheduler | Support | Release Notes mentioned in User Story 368113: Concurrency - Scheduler - Progress Note with all other | Low
368154 | 2023/05 | Ready for Deployment | 88 | Billing Invoice | Concurrency - Office Visit List - Check-out with all other actions | Basma Aslam | Concurrency of Scheduler and Flowsheet | Activity Based Scheduler | Support | Release Notes mentioned in User Story 368113: Concurrency - Scheduler - Progress Note with all other | Low
413616 | 2023/05 | Ready for Deployment | 89 | Billing Invoice | Electronic Signature 21 CFR Part 11 - Logging via URL and CureCam > eSuperbill | Ismail Suri | Code of Federal Regulation - Electronic Signature | Business Continuity - RM2022 | NA | Post Title: 21 CFR Part 11 Compliant Electronic SignaturesPost Description:21 CFR Part 11 is a regul | Low
374563 | 2023/05 | Ready for Deployment | 85 | Billing Invoice | Electronic Signature 21 CFR Part 11 Compliant Signature > eSuperbill | Aisha Qureshi | Code of Federal Regulation - Electronic Signature | Business Continuity - RM2022 | Client | Post Title: 21 CFR Part 11 Compliant Electronic Signatures > eSuperbill Post Description:With this e | Low
397502 | 2023/05 | Ready for Deployment | 87 | Billing Invoice | Log of Expert System on Merge eSuperbill | Farhan Ajmal | Logs | Billing Development | Support | With this enhancement in cureMD solution, RCM user will able to view the merge eSuperbill logs of Ex | Low
403317 | 2023/05 | Ready for Deployment | 88 | Billing Invoice | Plan Balance not Positioned properly on Patient Banner | Abdur Rehman Shamsi | Patient Banner - Billing Portion | Billing Development | NA | Fix of a Live issue, No release notes are needed for an already existing Implementation. | Low
374828 | 2023/05 | Approved | 84 | Billing Payments | nH Refund API - Implementation for Outstanding balances and advances (deductibles) | Maham Nasir Khan | Billing APIs | CureMD API | NA | With this modification in the refund API, the user should be able to refund a patient's outstanding | Low
402463 | 2023/05 | Ready for Deployment | 87 | Billing Payments | [Refactorization] As a Payment poster, I want collapsible grouping for ERA claims | Sohaib Shahid | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
402272 | 2023/05 | Ready for Deployment | 87 | Billing Payments | [Technical] Advance Allocation with different Appointment | Asad Rajpoot | Work queue structure for payments | Batch Payments | NA | This is a technical story. No release notes are required. | Low
387752 | 2023/05 | Ready for Deployment | 89 | Billing Payments | [Technical] Appointment Notes Logging in Audit Trail | Asad Rajpoot | Logs | Billing Development | NA | For the technical story, no release notes are needed. | Low
417322 | 2023/05 | Ready for Deployment | 89 | Billing Payments | [Technical] As a developer, I want to find and cater missing Copay scenarios in ERA batches | Abdur Rehman Shamsi | Reconciling items within batches | Batch Payments | NA | Attached with User Guide | Low
381695 | 2023/05 | Ready for Deployment | 85 | Billing Payments | [TECHNICAL] Avoid the deadlock while adding/update the payments | Asad Rajpoot | Payments | Billing Development | NA | It's the technical US. No release notes required. | Low
393466 | 2023/05 | Ready for Deployment | 86 | Billing Payments | [TECHNICAL] Avoid the deadlock while adding/update the payments | Saud Jamshaid | Payments | Billing Development | NA | It's the technical US. No release notes required. | Low
397842 | 2023/05 | Ready for Deployment | 87 | Billing Payments | [Technical] Exception Handling and File logging for import diagnosis | Asad Rajpoot | Diagnosis | Billing Development | NA | This is a technical story. No release notes are required. | Low
401549 | 2023/05 | Ready for Deployment | 87 | Billing Payments | [Technical] Rework of Payerid to Planid in batch payments | Ahmad Saleem | Work queue structure for payments | Batch Payments | NA | Attached with User Guide | Low
409458 | 2023/05 | Ready for Deployment | 88 | Billing Payments | [Technical] Rework of Payerid to Planid in batch payments | Sohaib Shahid | Work queue structure for payments | Batch Payments | NA | Attached with User Guide | Low
409252 | 2023/05 | Ready for Deployment | 88 | Billing Payments | [Testing] Ability to manually invoke TextToPay Service | Asad Rajpoot | Text 2 Pay | Payment processing integration with Global Payment Gateway | Client | Post Title: Ability to manually invoke Text To Pay ServicePost Description: With this enhancement in | Low
416134 | 2023/05 | Ready for Deployment | 89 | Billing Payments | [Testing] Ability to send Text to Pay after specified days | Abdur Rehman Shamsi | Text 2 Pay | Payment processing integration with Global Payment Gateway | Client | Post Title: Ability to send Text to Pay after specified daysPost Description: With this enhancement | Low
398366 | 2023/05 | Ready for Deployment | 87 | Billing Payments | Ability to manually invoke TextToPay Service | Abdur Rehman Shamsi | Text 2 Pay | Payment processing integration with Global Payment Gateway | Client | Post Title: Ability to manually invoke Text To Pay ServicePost Description: With this enhancement in | Low
395208 | 2023/05 | Ready for Deployment | 86 | Billing Payments | Ability to manually invoke TextToPay Service | Abdur Rehman Shamsi | Text 2 Pay | Payment processing integration with Global Payment Gateway | NA | Refer to User Story 398366: Ability to manually invoke TextToPay Service | Low
405916 | 2023/05 | Ready for Deployment | 88 | Billing Payments | Ability to Restrict Payment Posting Updates | Farhan Ajmal | Payments | RCM - RM2023 | Client | Post Title: Ability to Restrict Credit Card Payments PostingPost Description: With this enhancement | Low
406847 | 2023/05 | Ready for Deployment | 88 | Billing Payments | Ability to send Text to Pay after specified days | Abdur Rehman Shamsi | Text 2 Pay | Payment processing integration with Global Payment Gateway | NA | Refer to User Story 416134: [Testing] Ability to send Text to Pay after specified days | Low
393935 | 2023/05 | Ready for Deployment | 86 | Billing Payments | As a biller, I want to open specific appointment when I click on DOS | Abdur Rehman Shamsi | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
391906 | 2023/05 | Ready for Deployment | 86 | Billing Payments | As a biller, I want to see reason behind problematic and Non-postable claims | Abdur Rehman Shamsi | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
391743 | 2023/05 | Ready for Deployment | 86 | Billing Payments | As a biller, I want to view 835 ERA file with each payment | Abdur Rehman Shamsi | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
392305 | 2023/05 | Ready for Deployment | 86 | Billing Payments | As a biller, I want to view ERA report of each claim | Abdur Rehman Shamsi | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
345172 | 2023/05 | Ready for Deployment | 85 | Billing Payments | As a developer, I want to maintain an approval status for each batch separately | Ahmad Saleem | Reviewing and closing batches | Batch Payments | NA | Attached with User Guide | Low
405510 | 2023/05 | Ready for Deployment | 89 | Billing Payments | As a payment poster, I want a settings to enable/disable auto-verification of payments | Abdur Rehman Shamsi | Payment instrument tracking | Batch Payments | NA | Attached with User Guide | Low
395985 | 2023/05 | Ready for Deployment | 87 | Billing Payments | As a payment poster, I want an option to select next responsible party on each claim of a batch | Abdur Rehman Shamsi | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
409141 | 2023/05 | Ready for Deployment | 88 | Billing Payments | As a payment poster, I want an option to select next responsible party on each claim of a batch | Saud Jamshaid | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
382079 | 2023/05 | Ready for Deployment | 86 | Billing Payments | As a Payment poster, I want collapsible grouping for ERA claims | Abdur Rehman Shamsi | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
345166 | 2023/05 | Ready for Deployment | 84 | Billing Payments | As a payment poster, I want to add and view Reconciling Items against payment batches and claims wit | Ahmad Saleem | Reconciling items within batches | Batch Payments | NA | Attached with User Guide | Low
343836 | 2023/05 | Ready for Deployment | 83 | Billing Payments | As a payment poster, I want to add claims associated with a batch | Subhan Ahmad | Editing ERA claim associations and payments | Batch Payments | NA | Attached with User Guide | Low
387208 | 2023/05 | Ready for Deployment | 86 | Billing Payments | As a payment poster, I want to attach files with a Batch | Abdur Rehman Shamsi | Allowing attachments with batches | Batch Payments | NA | Attached with User Guide | Low
364907 | 2023/05 | Ready for Deployment | 82 | Billing Payments | As a payment poster, I want to be able to search for claims associated with an ERA batch | Subhan Ahmad | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
364909 | 2023/05 | Ready for Deployment | 82 | Billing Payments | As a payment poster, I want to be able to sort claims associated with a batch | Subhan Ahmad | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
403763 | 2023/05 | Ready for Deployment | 87 | Billing Payments | As a payment poster, I want to download attach files with a Batch | Saud Jamshaid | Allowing attachments with batches | Batch Payments | NA | Attached with User Guide | Low
357990 | 2023/05 | Ready for Deployment | 82 | Billing Payments | As a payment poster, I want to identify batches with problematic and non-postable claims on the batc | Subhan Ahmad | Work queue structure for payments | Batch Payments | NA | Attached with User Guide | Low
345157 | 2023/05 | Ready for Deployment | 83 | Billing Payments | As a payment poster, I want to make changes to claims and claim details associated with an ERA | Ahmad Saleem | Editing ERA claim associations and payments | Batch Payments | NA | Attached with User Guide | Low
375800 | 2023/05 | Ready for Deployment | 85 | Billing Payments | As a payment poster, I want to post payments for claims linked to batches from the batch details scr | Subhan Ahmad | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
395914 | 2023/05 | Ready for Deployment | 88 | Billing Payments | As a payment poster, I want to record adjustments codes against all claims in a batch on a CPT level | Abdur Rehman Shamsi | Reconciling items within batches | Batch Payments | NA | Attached with User Guide | Low
416216 | 2023/05 | Ready for Deployment | 89 | Billing Payments | As a payment poster, I want to record adjustments codes against all claims in a batch on a CPT level | Aroosha Farooq | Reconciling items within batches | Batch Payments | NA | Attached with User Guide | Low
370436 | 2023/05 | Ready for Deployment | 83 | Billing Payments | As a payment poster, I want to remove claims associated with a batch | Subhan Ahmad | Editing ERA claim associations and payments | Batch Payments | NA | Attached with User Guide | Low
380369 | 2023/05 | Ready for Deployment | 84 | Billing Payments | As a payment poster, I want to remove claims associated with a batch, removing any payments posted f | Subhan Ahmad | Editing ERA claim associations and payments | Batch Payments | NA | Attached with User Guide | Low
370417 | 2023/05 | Ready for Deployment | 84 | Billing Payments | As a payment poster, I want to remove Reconciling Items against payment batches | Subhan Ahmad | Reconciling items within batches | Batch Payments | NA | Attached with User Guide | Low
380921 | 2023/05 | Ready for Deployment | 85 | Billing Payments | As a payment poster, I want to see patient details on the banner of a claim | Abdur Rehman Shamsi | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
376049 | 2023/05 | Ready for Deployment | 84 | Billing Payments | As a payment poster, I want to view copay and modifier along with CPT level details for claims assoc | Subhan Ahmad | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
393517 | 2023/05 | Ready for Deployment | 86 | Billing Payments | As a payment poster, I want to view details of previous payments received against a service from the | Zaheer Abbas | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
355640 | 2023/05 | Ready for Deployment | 81 | Billing Payments | As a Practice User, I want to access and view all insurance payments on a single screen so that I ca | Aroosha Farooq | Work queue structure for payments | Batch Payments | NA | Attached in User Guide. | Low
355717 | 2023/05 | Ready for Deployment | 81 | Billing Payments | As a Practice User, I want to apply filters on columns on the ‘Batches Queue’ So that I can retriev | Aroosha Farooq | Enhanced filter and sorting options | Batch Payments | NA | Attached with User Guide | Low
355918 | 2023/05 | Ready for Deployment | 81 | Billing Payments | As a practice user, I want to assign batches to myself So that I can view tasks in my queue separate | Aroosha Farooq | Work queue structure for payments | Batch Payments | NA | Attached with User Guide | Low
345163 | 2023/05 | Ready for Deployment | 85 | Billing Payments | As a practice user, I want to mark the payment status against each batch | Ahmad Saleem | Payment instrument tracking | Batch Payments | NA | Attached with User Guide | Low
364800 | 2023/05 | Ready for Deployment | 82 | Billing Payments | As a practice user, I want to view all claims associated with an ERA batch | Subhan Ahmad | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
364804 | 2023/05 | Ready for Deployment | 82 | Billing Payments | As a practice user, I want to view all services associated with claims within an ERA batch | Subhan Ahmad | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
364899 | 2023/05 | Ready for Deployment | 82 | Billing Payments | As a practice user, I want to view header information relevant to ERA batches created | Subhan Ahmad | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
355651 | 2023/05 | Ready for Deployment | 81 | Billing Payments | As a practice user, I want to view summaries on the batches queue, based on filtered results | Aroosha Farooq | Reporting and summaries | Batch Payments | NA | Attached with User Guide | Low
342040 | 2023/05 | Ready for Deployment | 82 | Billing Payments | As a practice user, I want to view the settlement status of each batch | Subhan Ahmad | Reconciling payments with settlements | Batch Payments | NA | Attached with User Guide | Low
383085 | 2023/05 | Ready for Deployment | 85 | Billing Payments | As a product owner, I want Batch listing in tabular form with separate ERA and EOB tabs | Abdur Rehman Shamsi | Work queue structure for payments | Batch Payments | NA | Attached with User Guide | Low
405716 | 2023/05 | Ready for Deployment | 89 | Billing Payments | As a product owner, I want changes in UI and UX of Details and listing screens | Abdur Rehman Shamsi | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
382029 | 2023/05 | Ready for Deployment | 86 | Billing Payments | As a product owner, I want changes in UI and UX of Details screens | Abdur Rehman Shamsi | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
381710 | 2023/05 | Ready for Deployment | 85 | Billing Payments | As a product owner, I want changes in UI and UX of Listing screens | Abdur Rehman Shamsi | Work queue structure for payments | Batch Payments | NA | Attached with User Guide | Low
410323 | 2023/05 | Ready for Deployment | 88 | Billing Payments | As developers, we want to reduce our product's technical debt to improve our product quality (Import | Ahmad Saleem | 10g Services Technical Debt Removal | 10g Improvements | NA | This is a technical story. No release notes are required | Low
389998 | 2023/05 | Ready for Deployment | 86 | Billing Payments | As payment poster, I want to see settled/unsettled and Reconciling amount in the KPI on details scre | Abdur Rehman Shamsi | Batch details screen | Batch Payments | NA | Attached with User Guide | Low
387923 | 2023/05 | Ready for Deployment | 87 | Billing Payments | Audit Trial for CureBilling Page ¦ Missing scenarios | Abdur Rehman Shamsi | Curebilling Setting | RCM - RM2023 | NA | Refer to User Story 323767: Audit Trial for CureBilling page | Low
414749 | 2023/05 | Ready for Deployment | 89 | Billing Payments | Rework of Payerid to Planid in batch payments | Aroosha Farooq | Work queue structure for payments | Batch Payments | NA | Attached with User Guide | Low
405697 | 2023/05 | Ready for Deployment | 90 | Data Mining Reports | [HCFA Claims] Ability to see Log of Denials When Moved to Inprocess Bucket Through Resubmission | Abdur Rehman Shamsi | Logging/Procedure search at Denial Bucket | RCM - RM2022 | NA | This is a missing scenario of already implemented logs. No release notes needed. | Low
403328 | 2023/05 | Ready for Deployment | 90 | Data Mining Reports | Ability to search based on Preferred Language and Age in Months on Patient Search Report | Abdur Rehman Shamsi | Misc. | Business Continuity | Client | Post Title: Ability to search based on Preferred Language and Age in Months on Patient Search Report | Low
396722 | 2023/05 | Ready for Deployment | 90 | Data Mining Reports | Clinical Summary Report changes | Aisha Qureshi |  |  | NA | -- | Low
418052 | 2023/05 | Ready for Deployment | 90 | Data Mining Reports | Exclude Patients with PR-100 Adjustments from Patient Statements | Abdur Rehman Shamsi | Misc. | Business Continuity | Client | Post Title: Ability to Exclude Patients with PR-100 Adjustments from Patient StatementsPost Descript | Low
422044 | 2023/05 | Development | 90 | Quality Programs | Appointment Level Attachment Functionality on ADD Problem List | Farhan Ajmal | Problem List Resolution Automation | RCM - RM2023 | Support | With this enhancement in CureMD application, user will able to view the new design of add problem li | Low
396784 | 2023/05 | Ready for Deployment | 87 | Quality Programs | [Enhancement] As a Provider, I want to be able to view if a Patient qualifies for a MIPS CQM but the | Sheryl Manzoor | Quality - Registry 2020 | MIPS | Client | Displaying Incomplete Measures with Multiple StrataGIVEN: Quality Programs module is enabled for the | Low
353089 | 2023/05 | Ready for Deployment | 85 | Quality Programs | [Part 1: Backend] As a Provider, I want to be able to view if a Patient qualifies for a MIPS CQM but | Sheryl Manzoor | Quality - Registry 2020 | MIPS | Client | Post Title: Completing MIPS CQMs Documentation from the Patient ChartPost Description: With this enh | Low
390289 | 2023/05 | Ready for Deployment | 86 | Quality Programs | [Part 2: Frontend] As a Provider, I want to be able to view if a Patient qualifies for a MIPS CQM bu | Sheryl Manzoor | Quality - Registry 2020 | MIPS | Client | Post Title: Completing MIPS CQMs Documentation from the Patient ChartPost Description: With this enh | Low
406209 | 2023/05 | Ready for Deployment | 88 | Quality Programs | [Technical] As an analyst, I want to have all the issues resolved in the MIPS job for registry measu | Sheryl Manzoor | Quality - Registry 2020 | MIPS | Support | A release note does not need to be published on CureWiki for this user story. This user story was wr | Low
373060 | 2023/05 | Ready for Deployment | 87 | Quality Programs | [Technical] Removing yearly check for updating CCM Billing Procedure Codes Library | Sheryl Manzoor | Care Programs | MixPanel | Support | Note: Please do not publish this release note on CureWiki. This user story was written to remove yea | Low
412463 | 2023/05 | Ready for Deployment | 89 | Quality Programs | Add New Category in Problem List Issue Category dropdown List | Hamza Qaiser | Problem List Resolution Automation | RCM - RM2023 | Support | With this enhancement in CureMD application, RCM user will able to add the new issue category while | Low
397570 | 2023/05 | Ready for Deployment | 89 | Quality Programs | Appointment and Procedure wise Add Problem List Module Updates | Farhan Ajmal | Problem List Resolution Automation | RCM - RM2023 | Support | With this enhancement in CureMD application, user will able to view the new design of add problem li | Low
357440 | 2023/05 | Ready for Deployment | 86 | Quality Programs | As an analyst, I want the changes made to patient's qualification in MIPS CQMs from patient chart to | Sheryl Manzoor | Quality - Registry 2020 | MIPS | Client | Post Title: Displaying Changes Made to Patient's Qualification in MIPS CQMs from Patient Chart on th | Low
382856 | 2023/05 | Ready for Deployment | 87 | Quality Programs | Billing: Expert System's Warning/Error workflow updates on eSuperbill | Farhan Ajmal | Expert System Enhancements | RCM - RM2023 | Support | With this enhancement in CureMD application, user will able to sign the eSuperbill when Expert Syste | Low
373845 | 2023/05 | Ready for Deployment | 88 | Quality Programs | Bulk Actions on Problem List | Rabia Shahid | Problem List Resolution Automation | RCM - RM2023 | Client | With this enhancement in CureMD application. Practice User will able to perform bulk action on probl | Low
396968 | 2023/05 | Ready for Deployment | 87 | Quality Programs | Default Provider on Quick Esuperbill | Abdur Rehman Shamsi | eSuperbills | Billing Development | Client | Post Title: Default Provider unselected on Quick eSuperbillPost Description: With this enhancement i | Low
366633 | 2023/05 | Ready for Deployment | 86 | Quality Programs | Moving the appointment to OnHold when adding a Comment on a Problem from the Problem List | Muhammad Mobeen | Problem List Resolution Automation | RCM - RM2023 | Support | With this enhancement in CureMD Application, system will move the appointment automatically to on ho | Low
399893 | 2023/05 | Ready for Deployment | 87 | Quality Programs | Moving the appointment to OnHold when adding all comments or Actions | Farhan Ajmal | Problem List Resolution Automation | RCM - RM2023 | Client | With this enhancement in CureMD application, user will able to move the appointment or procedure lev | Low
397201 | 2023/05 | Ready for Deployment | 87 | Quality Programs | Need to add URL as an attachment in Problem List | Farhan Ajmal | Problem List Resolution Automation | RCM - RM2023 | Support | With this enhancement in CureMD application, user will able to attach the URL as an attachment. Curr | Low
360314 | 2023/05 | Ready for Deployment | 89 | Quality Programs | Need to enable E&M Calculator and MDM method for 99252-99255: Inpatient Consultations | Farhan Ajmal | Hospital Inpatient Categories Updates for 2023 | Evaluation and Management - 2023 | Client | Post Title: Enable E&M Method for inpateint Consultation CategoryPost Description: With this enhance | Low
395950 | 2023/05 | Ready for Deployment | 88 | Quality Programs | Need to Update Problem List Category Dropdown | Farhan Ajmal | Problem List Resolution Automation | RCM - RM2023 | Support | With this enahancement in CureMD application, User will able to search the Issue Categories while ad | Low
374177 | 2023/05 | Ready for Deployment | 87 | Quality Programs | Oncology Performance Status Assessment Forms in v10 | Abdur Rehman Shamsi | Enhancements in Assessment Component - Graphical Overview - Trend Charts | Roadmap 2022 | Client | Post Title: Ability to Record Oncology Performance Status in 10gPost Description: With this enhancem | Low
408241 | 2023/05 | Ready for Deployment | 88 | Quality Programs | SonarQube bug fixing | Rabia Shahid | Technical Debt - SonarQube bugs removal | 10g Improvements | NA | N/A | Low